WEEK 1: Project Review and Development Planning

INTENDED LEARNING OUTCOME

At the end of this activity, students should be able to:

Develop a comprehensive project implementation plan by reviewing the approved capstone proposal, validating project scope, incorporating panel recommendations, assigning project responsibilities, preparing a project schedule, and establishing project monitoring tools.

OVERVIEW OF WEEK 1 OUTPUTS

By the end of Week 1, each group must submit:

- Panel Recommendation Compliance Matrix

- Project Scope Validation Form

- Work Breakdown Structure (WBS)

- Revised Gantt Chart

- Project Development Plan

- Repository Setup Report

- Adviser Consultation Record

ACTIVITY 1

Review of Panel Recommendations

Purpose

To ensure that all recommendations from the proposal defense have been reviewed and addressed before implementation begins.

Procedure

- Secure a copy of the proposal defense evaluation sheet.

- Review all comments from the panel.

- Discuss as a group how each recommendation will be addressed.

- Complete Form 1.

FORM 1

PANEL RECOMMENDATION COMPLIANCE MATRIX

Instructions

For every recommendation:

- Copy the recommendation exactly as stated by the panel.

- Describe the action that the group will take.

- Identify supporting evidence.

- Mark the status.

| No. | Panel Recommendation | Planned Action | Evidence | Status |
| --- | --- | --- | --- | --- |
| 1 | To include in the Background of the Project the real concern of scenario where a certain individual connecting to public wi-fi and unauthorized hacking was experienced. | Add a real-life scenario in the Background of the Project discussing the risks of connecting to Public Wi-Fi, including a case of unauthorized access/hacking. | This is incorporated on pages 4-5 of the manuscript. | Completed |
| 2 | Revise Specific Objectives, incorporated in the paper. | Revise and refine the specific objectives to improve clarity and alignment with the study. | The updated objectives are presented on pages 9-10 of the manuscript. | Completed |
| 3 | Revise RRL by categorizing related topics. | Revise the RRL by organizing and categorizing sources according to relevant themes. | The organized and categorized RRL are found on pages 15–22 of the manuscript. | Completed |
| 4 | Emphasis on the synthesis the existing study and how the project surpass the existing literature. | Revise the synthesis to emphasize the integration of existing studies and clearly highlight how the proposed system surpasses current literature. | The updated synthesis is reflected on pages 26–29 of the manuscript. | Completed |
| 5 | Revise methodology based on the objectives. | Revise the methodology to ensure alignment with the stated objectives. | The revised methodology is presented on pages 30–43 of the manuscript. | Completed |
| 6 | Define Public Wi-Fi | Add a clear definition of Public Wi-Fi in the manuscript to establish context for the study. | The definition is presented on pages 2-3. | Completed |
| 7 | Use hierarchical numbering format (1.1, 1.2) instead of a, b, c | Reformat objectives using hierarchical numbering to improve clarity and comply with panel instructions. | The revision is reflected on page 9-10 of the manuscript. | Completed |
| 8 | Related studies are summarized individually without direct cross-comparison. A Comparative Analysis table is needed with a "Relevance to the Proposed System" column to show how the study builds on existing literature. | Add and develop Table 1 (Comparative Analysis of Related Studies) with columns for Author/Year, Method/Tool, Threats Detected, Strengths, Limitations, and Relevance to the Proposed System. | Updated table found on pages 25-26. | Completed |
| 9 | TP, FP, TN, and FN definitions are present in the manuscript but not formatted as a properly labeled table, making IDS evaluation criteria unclear for readers and panel reviewers. | Add a titled confusion matrix table ("Table. Confusion Matrix Terms for IDS Evaluation") in Section 3.6 defining TP, FP, TN, FN, Detection Rate, False Positive Rate, and Mean Response Time. | Updated section is on pages 40–43. | Completed |
| 10 | Objective 4 states the False Positive Rate target as "not exceeding 5%", but Chapter III (Sections 3.5 and 3.6) and Chapter IV (Section 4.6.3) do not clearly repeat or apply this benchmark consistently. | Add the explicit benchmark "False Positive Rate target: not exceeding 5%" to Section 3.5 (Evaluation Procedure), Section 3.6 (Data Analysis Techniques), and Section 4.6.3 (Security Metrics) to ensure consistency across all chapters. | See pages 38, 40, and 62 of the manuscript. | Completed |
| 11 | Attack simulation procedures do not specify the exact number of trials per attack type, nor is there a structured testing matrix linking each attack to the tool used, expected detection, severity level, and metric recorded. | Specify 5 trials per attack type in Section 3.5 (Alpha Testing) and Section 4.6 (Attack Simulation). Add a testing matrix in Section 4.6.3: Attack Type → Tool Used → Expected Detection → Severity → Metric Recorded. | See pages 38, 60 and 62-65. | Completed |
| 12 | Metrics of measurement and success were not included in the objectives | Incorporate measurable indicators of success into the objectives to ensure clarity and evaluability. | The revised objectives are presented on page 10, 4.1-4.3 of the specific objectives. | Completed |
| 13 | Identification of devices connected in terms of? | Clarify the identification of devices connected to the public Wi-Fi network by specifying the parameters used like IP address, MAC address, and device-related information. | The revised objective is reflected on page 9, 1.1 of the specific objectives. | Completed |
| 14 | Accuracy – How to measure threshold value? | Clarify the basis for threshold values used in threat detection and defined how accuracy is measured using detection rate, false positive rate, and response time. | The revisions are reflected on page 10, no.4 of the specific objectives. | Completed |
| 15 | Identify network behavior | Address the identification of network behavior by incorporating features for capturing, analyzing, and monitoring real-time network activities, particularly under Objectives 1.3 and 1.4. | These enhancements are reflected on page 9 of the manuscript. | Completed |
| 16 | Emphasize specific threats (MITM, ARP poisoning, MAC spoofing, port scanning) | Add a clear definition and explanation of the four major network threats in the Background section to clearly emphasize their relevance to public Wi-Fi security. | The definition and explanation are reflected on page 3, 2nd paragraph. | Completed |
| 17 | Include actual damages and risks based on literature and actual data | Incorporate discussion of real-world consequences such as identity theft, financial loss, and unauthorized access based on news reports and literature. | This is incorporated on page 4. | Completed |
| 18 | Show how accuracy is tested | Include testing procedures describing how detection accuracy, false positive rate, and response time are evaluated using simulated attacks. | These inclusions are reflected in phase 3, page 31. | Completed |

ACTIVITY 2

Project Scope Validation

Purpose

To verify that the approved project remains feasible and aligned with client requirements.

Procedure

- Review Chapter 1 and Chapter 3.

- Verify all objectives.

- Review scope and limitations.

- Identify any requested modifications.

- Complete Form 2.

FORM 2

PROJECT SCOPE VALIDATION FORM

Instructions

Check whether each component remains valid.

A. Objectives Validation

| Objective | Still Applicable? | Remarks |
| --- | --- | --- |
| Objective 1: Design and develop a real-time network monitoring system | Yes | Covers device identification by IP address, MAC address, hostname, vendor, and connection status; logging of connection and disconnection events; packet capture and analysis using Npcap and Scapy; detection of abnormal network behavior such as ARP inconsistencies, MAC spoofing, and unusual TCP patterns; and real-time alerts with audible and visual indicators and mitigation recommendations. Still applicable — all sub-objectives (1.1–1.5) remain feasible on a Windows host machine. |
| Objective 2: Develop a web-based monitoring dashboard | Yes | Displays real-time network activity and device information, shows detected threats with severity classification, and supports filtering, logging, and report generation. Still applicable — Flask and Flask-SocketIO remain the approved stack, and the dashboard runs on localhost (127.0.0.1) as stated in the Scope and Limitations. |
| Objective 3: Implement a threat detection and classification mechanism for Man-in-the-Middle attacks, ARP poisoning, MAC spoofing, and port scanning | Yes | Rule-based detection using gateway MAC anomaly checking, IP-to-MAC mapping conflict detection, duplicate MAC monitoring, and a TCP connection threshold of more than 15 unique destination ports within 30 seconds. Still applicable — the detection scope remains limited to the four approved threat types; no additional attack types were added. |
| Objective 4: Evaluate the system's performance using Detection Rate, False Positive Rate, and Mean Response Time | Yes | Targets are a Detection Rate of 1.0, a False Positive Rate not exceeding 5%, and a Mean Response Time of 5–15 seconds. Still applicable — these benchmarks are now stated consistently in Sections 3.5, 3.6, and 4.6.3 following panel recommendation No. 10. |
| Objective 5: Conduct controlled network security testing through authorized attack simulation | Yes | Covers validation of packet capture accuracy, assessment of the rule-based detection mechanism, evaluation of severity classification and real-time alert generation, and measurement of response time and detection consistency across trials. Still applicable — five trials per attack type will be conducted within the authorized test network at JR Inasal House – Alicia Branch, with permission from establishment management. |

B. Requirements Validation

| Requirement | Validated | Remarks |
| --- | --- | --- |
| Functional Requirements | ☑ | Validated. Device discovery and identification (IP address, MAC address, hostname, vendor, status), connection and disconnection logging, real-time packet capture, rule-based detection of the four target threats, severity classification, audible and visual alerts, mitigation recommendations, log filtering, report export, and administrator authentication. |
| Non-Functional Requirements | ☑ | Validated. Detection Rate target of 1.0, False Positive Rate not exceeding 5%, and Mean Response Time of 5–15 seconds; passive and non-disruptive monitoring; localhost-only dashboard access; bcrypt-hashed credentials; overall quality assessed using ISO/IEC 25010:2011 characteristics. |
| User Requirements | ☑ | Validated. Primary users are the Manager and two frontline staff of JR Inasal House – Alicia Branch. The dashboard uses plain-language alerts and mitigation guidance so it can be operated without deep technical expertise. |
| Hardware Requirements | ☑ | Validated. Windows-based administrator monitoring computer with a wireless adapter capable of promiscuous mode; Kali Linux machine for authorized attack simulation; the establishment's existing wireless router / access point; client devices (smartphones and laptops). |
| Software Requirements | ☑ | Validated. Python 3, Flask, Flask-SocketIO, Scapy, Npcap, SQLite, and a web browser. Authorized testing tools: Nmap, arpspoof (dsniff), arping, and ip link on Kali Linux. |

C. Scope Changes

List proposed modifications.

| Proposed Change | Reason | Adviser Approval |
| --- | --- | --- |
| No change in the approved scope of the study. | The general and specific objectives, the four target threat types, the deployment site, and the evaluation framework all remain feasible and unchanged after the proposal defense. | For adviser confirmation |
| Addition of dashboard threat analytics (Chart.js visualization) and a threat acknowledge / resolve function. | Improves usability and supports the ISO/IEC 25010 Usability and Functional Suitability evaluation. It does not expand the detection scope or add new attack types. | For adviser confirmation |
| Addition of application-layer security hardening (CSRF protection and login rate limiting). | Strengthens administrator access control consistent with the ISO/IEC 27001:2022 principles already cited in the manuscript. | For adviser confirmation |

ACTIVITY 3

Work Breakdown Structure Development

Purpose

To organize all project activities and distribute responsibilities among team members.

Procedure

- List all tasks needed to complete the project.

- Group similar tasks together.

- Assign responsible members.

- Estimate completion dates.

- Complete Form 3.

FORM 3

WORK BREAKDOWN STRUCTURE (WBS)

Instructions

Break down project activities into smaller work packages.

| Major Deliverable | Task | Assigned Member | Due Week |
| --- | --- | --- | --- |
| Front-End Development | Login Interface | Bueno, Jannces G. | Week 2 |
| Front-End Development | Dashboard layout and navigation structure | Bueno, Jannces G. | Week 2 |
| Front-End Development | Live device monitoring table (IP, MAC, hostname, vendor, status) | Bueno, Jannces G. | Week 3 |
| Front-End Development | Threat intelligence log panel with severity color coding | Bueno, Jannces G. | Week 4 |
| Front-End Development | Network connection log and administrator activity log views | Bueno, Jannces G. | Week 4 |
| Front-End Development | Real-time alert interface (audible alarm and color-flash indicator) | Bueno, Jannces G. | Week 5 |
| Front-End Development | Threat log filtering, report export, and change password interface | Bueno, Jannces G. | Week 5 |
| Back-End Development | Authentication Module (bcrypt hashing, session control, login rate limiting, CSRF protection) | Bueno, Jannces G. | Week 2 |
| Back-End Development | Packet capture module using Scapy and Npcap | Bueno, Jannces G. | Week 3 |
| Back-End Development | Device registry, liveness prober, and connection event logging | Bueno, Jannces G. | Week 3 |
| Back-End Development | Rule-based detection engine for MITM, ARP poisoning, MAC spoofing, and port scanning | Bueno, Jannces G. | Weeks 4–6 |
| Back-End Development | Severity classification and mitigation recommendation mapping | Bueno, Jannces G. | Week 6 |
| Back-End Development | Flask-SocketIO real-time event push and alert dispatch | Bueno, Jannces G. | Week 6 |
| Back-End Development | Report export endpoint and administrator action logging | Bueno, Jannces G. | Week 7 |
| Database Development | Database Creation (devices, threats, connection_log, admin_users, admin_log) | Bueno, Jannces G. | Week 2 |
| Database Development | Schema initialization script and threat deduplication logic | Bueno, Jannces G. | Week 3 |
| Database Development | Data integrity checking and database backup procedure | Bueno, Jannces G. | Week 7 |
| Testing | Unit Testing of each detection rule | Gulla, Ma. Leonora M. | Week 7 |
| Testing | Integration and smoke testing of the dashboard and back-end modules | Gulla, Ma. Leonora M. | Week 8 |
| Testing | Baseline normal traffic observation for True Negative and False Positive Rate computation | Gulla, Ma. Leonora M. | Week 9 |
| Testing | Alpha Testing – five authorized attack trials per attack type using Kali Linux | Gulla, Ma. Leonora M. | Weeks 9–11 |
| Testing | Beta Testing – on-site operational validation at JR Inasal House – Alicia Branch | Gulla, Ma. Leonora M. | Weeks 12–13 |
| Evaluation | Guided demonstration and user evaluation with the Manager and two frontline staff | All members | Week 14 |
| Evaluation | Computation of Detection Rate, False Positive Rate, Mean Response Time, and Weighted Mean | Bueno, Jannces G. | Week 15 |
| Deployment | Installation on the administrator machine and database initialization | Bueno, Jannces G. | Week 13 |
| Deployment | Environment preparation (Python 3, Flask, Scapy, Npcap, dependencies) | Bueno, Jannces G. | Week 12 |
| Deployment | Verification of all system features in the live network environment | All members | Week 13 |
| Documentation | User Manual | Attaban, Quincy Joy B. | Week 15 |
| Documentation | Weekly activity forms and progress documentation | Attaban, Quincy Joy B. | Weeks 1–18 |
| Documentation | Preparation and expert validation of the ISO/IEC 25010 evaluation questionnaire | Attaban, Quincy Joy B. | Week 13 |
| Documentation | Chapter IV–V write-up (results, discussion, conclusions, and recommendations) | Attaban, Quincy Joy B. | Weeks 15–16 |
| Documentation | Preparation of mock defense presentation materials | Attaban, Quincy Joy B. | Week 16 |
| Documentation | Final manuscript revision and final defense preparation | All members | Weeks 17–18 |

Team Verification

All members must sign below:

ACTIVITY 4

Gantt Chart Preparation

Purpose

To establish a semester-long implementation schedule.

Procedure

- Use the completed WBS.

- Identify project milestones.

- Assign target weeks.

- Prepare the schedule.

- Complete Form 4.

FORM 4

GANTT CHART SUBMISSION FORM

Instructions

Indicate when each task will be performed.

| Activities | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Development |  | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |
| Testing |  |  |  |  |  |  | X | X | X | X | X | X | X |  |  |  |  |  |
| Deployment |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |
| Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |
| Documentation | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |

Milestone Schedule

| Milestone | Target Week |
| --- | --- |
| Alpha Version | Week 9 |
| Prototype Presentation | Week 10 |
| Beta Version | Week 12 |
| Agency Immersion | Weeks 12–13 |
| Deployment | Week 13 |
| Evaluation | Weeks 14–15 |
| Mock Defense | Week 16 |
| Final Defense | Week 18 |

ACTIVITY 5

Development Planning

Purpose

To prepare the overall implementation strategy.

Procedure

- Determine development methodology.

- Identify technologies.

- Assign project roles.

- Identify risks.

- Complete Form 5.

FORM 5

PROJECT DEVELOPMENT PLAN

A. Team Roles

| Team Member | Role | Responsibilities |
| --- | --- | --- |
| Bueno, Jannces G. | Project Leader / Lead Developer | Overall project management and task monitoring; development of the front-end dashboard, back-end modules, packet capture, rule-based detection engine, severity classification, authentication and security controls, and the SQLite database; system deployment and computation of the evaluation metrics; primary liaison with the adviser and the establishment. |
| Attaban, Quincy Joy B. | Documentation | Preparation and maintenance of all project documentation, including the weekly activity forms, the ISO/IEC 25010 evaluation questionnaire, the user manual, the manuscript write-up, and the mock and final defense presentation materials. |
| Gulla, Ma. Leonora M. | Quality Assurance | Unit, integration, and smoke testing of all modules; baseline normal traffic observation; conduct of the authorized attack simulations during Alpha Testing and on-site Beta Testing; recording of results in the Technical Testing Log. |

B. Development Methodology

□ Agile

□ Scrum

☑ Waterfall – specifically the V-Model, in which every development stage is paired with a corresponding testing stage (Requirement Analysis, System Design, Implementation, Testing, and Deployment), as specified in Section 3.2 of the approved manuscript.

□ Incremental

C. Development Tools

| Category | Tool |
| --- | --- |
| Programming Language | Python 3 (back-end); HTML, CSS, and JavaScript (front-end) |
| Framework | Flask and Flask-SocketIO; Scapy with Npcap for packet capture; Chart.js for dashboard visualization |
| Database | SQLite 3 (wifi_guardian.db) |
| IDE | Visual Studio Code |
| Repository | GitHub (https://github.com/jannces/Capstone2) |

D. Risk Management Plan

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Limited packet visibility caused by access point client isolation or a wireless adapter that does not fully support promiscuous mode. | High | High | Verify adapter capability before deployment; supplement Scapy sniffing with ARP probing and DHCP/mDNS/LLMNR discovery; document visibility limits as a stated limitation of the study. |
| False positives from legitimate MAC or IP address changes, such as device MAC randomization or DHCP lease renewal. | Medium | Medium | Conduct baseline normal traffic observation; tune the detection thresholds; apply the five-minute deduplication window; monitor the False Positive Rate against the ≤ 5% benchmark. |
| Disruption of the establishment's normal operations or customer connectivity during on-site testing. | Low | High | Keep all monitoring passive; secure written permission from management; schedule testing during off-peak hours; prepare rollback procedures to restore normal network conditions immediately. |
| Loss of source code, database records, or documentation due to hardware failure, or schedule delays caused by member unavailability. | Medium | High | Commit to the GitHub repository after every working session; keep versioned backups of the database and manuscript; follow the WBS with buffer weeks and hold twice-weekly team meetings. |

E. Communication Plan

| Activity | Schedule |
| --- | --- |
| Team Meeting | Twice a week (Tuesday and Friday) for progress review and task assignment, with daily coordination through the group chat. |
| Adviser Consultation | Weekly consultation with the adviser, Romero Dante C. Salum, DIT, or as scheduled based on his availability; each session is recorded in the Adviser Consultation Record. |
| Client Coordination | Coordination with the Manager of JR Inasal House – Alicia Branch at least twice a month, with on-site visits during deployment, beta testing, and user evaluation. |

ACTIVITY 6

Repository Setup

Purpose

To establish version control and project collaboration mechanisms.

Procedure

- Create repository.

- Create project folder structure.

- Add all members.

- Commit initial files.

- Complete Form 6.

FORM 6

REPOSITORY SETUP REPORT

Repository Information

Repository Name:          Capstone2

Repository URL:        https://github.com/jannces/Capstone2

Member Access

| Member | Access Granted |
| --- | --- |
| Bueno, Jannces G. | Yes |
| Attaban, Quincy Joy B. | Yes |
| Gulla, Ma. Leonora M. | Yes |

Required Screenshots

Attach:

□ Repository Homepage

□ Team Members

□ Folder Structure

□ Initial Commit

Repository Structure

List folders created.

| Folder Name | Purpose |
| --- | --- |
| /docs | Documentation – manuscript, weekly forms, diagrams, and user manual |
| /database | Database Scripts – SQLite schema, initialization script, and backups |
| /frontend | Interface Development – HTML, CSS, JavaScript, and dashboard templates |
| /backend | Server-side Development – Flask application, packet capture, and detection engine |

ACTIVITY 7

Adviser Consultation

Purpose

To validate project readiness before development starts.

Procedure

- Present all Week 1 outputs.

- Discuss project schedule.

- Discuss risks and responsibilities.

- Record adviser recommendations.

- Complete Form 7.